## Aug 10, 2017
Test case plan
2017-08-10
# | Functionality | Scenario | Description | Notes | Tested by | Android 4.0 (Emulator) | Android 4.1 (Emulator) | Samsung Tablet S2
1 | Startup | App loads |  |  |  | Passed | Passed | Passed
2 | Food Resources |  | Add food resources |  |  | Passed | Passed | Passed
3 | Database | database | SQLite DB setup |  |  | In Progress | In Progress | In Progress
4 | Search Page | Search Activity | Add Search Activity and Search Fragment |  |  | Not Complete | Not Complete | Not Complete
5 |  | Search Result Activity | Create Search Result Fragment |  |  | Not Complete | Not Complete | Not Complete
|  | Chips for searhching | Chips for narrowing down user preferences |  |  | Not Complete | Not Complete | Not Complete
|  | Favorite Icon | Toggle functionality | User are able to track the food they like |  | Not Complete | Not Complete | Not Complete
|  | Food card | Custom Array adapter |  |  | Not Complete | Not Complete | Not Complete
6 | Main Activity | Random Selector | Random Picker for food |  |  | Not Complete | Not Complete | Not Complete
|  | Menu Navigation Drawer | Menu Navigation Drawer for each functionality |  |  | Not Complete | Not Complete | Not Complete

## Aug 11, 2017
Test case plan
2017-08-11
# | Functionality | Scenario | Description | Notes | Tested by | Android 4.0 (Emulator) | Android 4.1 (Emulator) | Samsung Tablet S2
1 | Startup | App loads |  |  |  | Passed | Passed | Passed
2 | Food Resources |  | Add food resources |  |  | Passed | Passed | Passed
3 | Database | database | SQLite DB setup |  |  | In Progress | In Progress | In Progress
4 | Search Page | Search Activity | Add Search Activity and Search Fragment |  |  | In Progress | In Progress | In Progress
5 |  | Search Result Activity | Create Search Result Fragment |  |  | Not Complete | Not Complete | Not Complete
|  | Chips for searhching | Chips for narrowing down user preferences |  |  | Not Complete | Not Complete | Not Complete
|  | Favorite Icon | Toggle functionality | User are able to track the food they like |  | Not Complete | Not Complete | Not Complete
|  | Food card | Custom Array adapter |  |  | Not Complete | Not Complete | Not Complete
6 | Main Activity | Random Selector | Random Picker for food |  |  | Not Complete | Not Complete | Not Complete
|  | Menu Navigation Drawer | Menu Navigation Drawer for each functionality |  |  | Not Complete | Not Complete | Not Complete

## Aug 13, 2017
Test case plan
2017-08-13
# | Functionality | Scenario | Description | Notes | Tested by | Android 4.0 (Emulator) | Android 4.1 (Emulator) | Samsung Tablet S2
1 | Startup | App loads |  |  |  | Passed | Passed | Passed
2 | Food Resources |  | Add food resources |  |  | Passed | Passed | Passed
3 | Database | database | SQLite DB setup |  |  | In Progress | In Progress | In Progress
4 | Search Page | Search Activity | Add Search Activity and Search Fragment |  |  | Passed | Passed | Passed
5 |  | Search Result Activity | Create Search Result Fragment |  |  | Passed | Passed | Passed
|  | Chips for searhching | Chips for narrowing down user preferences |  |  | Passed | Passed | Passed
|  | Favorite Icon | Toggle functionality | User are able to track the food they like |  | Passed | Passed | Passed
|  | Food card | Custom Array adapter |  |  | In Progress | In Progress | In Progress
6 | Main Activity | Random Selector | Random Picker for food |  |  | Not Complete | Not Complete | Not Complete
|  | Menu Navigation Drawer | Menu Navigation Drawer for each functionality |  |  | Not Complete | Not Complete | Not Complete

## Aug 14, 2017
Test case plan
2017-08-14
# | Functionality | Scenario | Description | Notes | Tested by | Android 4.0 (Emulator) | Android 4.1 (Emulator) | Samsung Tablet S2
1 | Startup | App loads |  |  |  | Passed | Passed | Passed
2 | Food Resources |  | Add food resources |  |  | Passed | Passed | Passed
3 | Database | database | SQLite DB setup |  |  | Passed | Passed | Passed
4 | Search Page | Search Activity | Add Search Activity and Search Fragment |  |  | Passed | Passed | Passed
5 |  | Search Result Activity | Create Search Result Fragment |  |  | Passed | Passed | Passed
|  | Chips for searhching | Chips for narrowing down user preferences |  |  | Passed | Passed | Passed
|  | Favorite Icon | Toggle functionality | User are able to track the food they like |  | Passed | Passed | Passed
|  | Food card | Custom Array adapter |  |  | In Progress | In Progress | In Progress
6 | Main Activity | Random Selector | Random Picker for food |  |  | Not Complete | Not Complete | Not Complete
|  | Menu Navigation Drawer | Menu Navigation Drawer for each functionality |  |  | Not Complete | Not Complete | Not Complete

## Aug 18, 2017
Test case plan
2017-08-18
# | Functionality | Scenario | Description | Notes | Tested by | Android 4.0 (Emulator) | Android 4.1 (Emulator) | Samsung Tablet S2
1 | Startup | App loads |  |  |  | Passed | Passed | Passed
2 | Food Resources |  | Add food resources |  |  | Passed | Passed | Passed
3 | Database | database | SQLite DB setup |  |  | Passed | Passed | Passed
4 | Search Page | Search Activity | Add Search Activity and Search Fragment |  |  | Passed | Passed | Passed
5 |  | Search Result Activity | Create Search Result Fragment |  |  | Passed | Passed | Passed
|  | Chips for searhching | Chips for narrowing down user preferences |  |  | Passed | Passed | Passed
|  | Favorite Icon | Toggle functionality | User are able to track the food they like |  | Passed | Passed | Passed
|  | Food card | Custom Array adapter |  |  | Passed | Passed | Passed
6 | Main Activity | Random Selector | Random Picker for food |  |  | Passed | Passed | Passed
|  | Menu Navigation Drawer | Menu Navigation Drawer for each functionality |  |  | Passed | Passed | Passed